## PakWheels_ Measures-Guideline F
# | Project / Organization Objective | Created Date (MM/DD/YYYY) | Year Month (YYYY-MM) | Measurement Detail (Objective) | CMMI Process Area | Quantified Objective (Desired) | Information Need (Source) | Base Information (Actual) | Analysis on measurement (How to improve?) | Objective Achieved? (Calculated field) | Corrective Action Plan
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-02 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | Yes | as per need
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-04 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes | as per need
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-05 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-01-06 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-01-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A |  |  |  |  | N/A (by Sprint)
10 | Achieve process excellence | 2018-03-15 | 2019-01-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-01-09 | Number of tasks which exceeded original estimate | PP | N/A |  |  |  |  | Depends
12 | Achieve process excellence | 2018-03-15 | 2019-01-10 | Project audit score | PPQA | 90 |  | 95 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-01-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-01-12 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-01-13 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-01-14 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes | perday depends on tasks
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-01-15 | Coding Practice Review score | VER | N/A |  |  |  |  | Discussion
20 | Achieve process excellence | 2018-03-15 | 2019-01-16 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes | AWS Services
2019-02-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Score of TPR in a month | VER | 90 |  | 95
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of risks occurred in a month | RSKM | 0 |  | 0
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of customer escalations in a month | VER | 2 |  | 0
6 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0
7 | Achieve process excellence | 2018-03-15 | 2019-02-15 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1
11 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Project audit score | PPQA | 90 |  | 95
13 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0
18 | Promote best coding practices among peers | 2018-03-15 | 2019-02-15 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-02-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2
2019-03-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 3 |  | No | QA team should run sanity wihout any sprint to identify all the bugs
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | No
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of risks occurred in a month | RSKM | 0 |  | 0
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of customer escalations in a month | VER | 2 |  | 3 |  | No | QA team should run sanity wihout any sprint to identify all the bugs
6 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-03-28 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 2 |  | No | Should lock the requirements changes (Before Sprint Planning)
11 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-03-28 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-03-28 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes
2019-04-01
1 | Achieve excellence in test coverage | 2018-05-17 | 2019-04-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 1 |  | Yes
2 | Achieve excellence in test coverage | 2018-05-17 | 2019-04-01 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-05-17 | 2019-04-01 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2018-05-17 | 2019-04-01 | Number of risks occurred in a month | RSKM | 0 |  | 0
5 | Achieve high customer satisfaction | 2018-05-17 | 2019-04-01 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-05-17 | 2019-04-01 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 4 |  | No | Should lock the requirements changes (Before Sprint Planning)
11 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-05-17 | 2019-04-01 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-05-17 | 2019-04-01 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-05-17 | 2019-04-01 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-05-17 | 2019-04-01 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-05-17 | 2019-04-01 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes
2019-08-01
1 | Achieve excellence in test coverage | 2019-09-06 | 2019-08-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2019-09-06 | 2019-08-01 | Score of TPR in a month | VER | 90 |  | Green |  | Yes
3 | Achieve high customer satisfaction | 2019-09-06 | 2019-08-01 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2019-09-06 | 2019-08-01 | Number of risks occurred in a month | RSKM | 0 |  | 0
5 | Achieve high customer satisfaction | 2019-09-06 | 2019-08-01 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2019-09-06 | 2019-08-01 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 0 |  | Yes
11 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2019-09-06 | 2019-08-01 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2019-09-06 | 2019-08-01 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2019-09-06 | 2019-08-01 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2019-09-06 | 2019-08-01 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2019-09-06 | 2019-08-01 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes

## Sheet1
# | Project / Organization Objective | Created Date (MM/DD/YYYY) | Year Month (YYYY-MM) | Measurement Detail (Objective) | CMMI Process Area | Quantified Objective (Desired) | Information Need (Source) | Base Information (Actual) | Analysis on measurement (How to improve?) | Objective Achieved? (Calculated field) | Corrective Action Plan
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-02 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | Yes | as per need
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-04 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes | as per need
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-05 | Number of customer escalations in a month | VER | 0 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-01-06 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-01-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A |  |  |  |  | N/A (by Sprint)
10 | Achieve process excellence | 2018-03-15 | 2019-01-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 0 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-01-09 | Number of tasks which exceeded original estimate | PP | N/A |  | 0 |  | Yes | Depends
12 | Achieve process excellence | 2018-03-15 | 2019-01-10 | Project audit score | PPQA | 90 |  | 95 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-01-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-01-12 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-01-13 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-01-14 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 1 |  | No | perday depends on tasks
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-01-15 | Coding Practice Review score | VER | N/A |  |  |  |  | Discussion
20 | Achieve process excellence | 2018-03-15 | 2019-01-16 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  |  |  |  | AWS Services
2019-02-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | No
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | No
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of customer escalations in a month | VER | 2 |  | 0 |  | No
6 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | No
7 | Achieve process excellence | 2018-03-15 | 2019-02-15 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Project audit score | PPQA | 90 |  | 95 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-02-15 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-02-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes
2019-03-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Score of TPR in a month | VER | 90 |  | 93 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-03-28 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-03-28 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-03-28 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  | N/A |  | Yes
2019-04-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-04-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-04-02 | Score of TPR in a month | VER | 90 |  | 91 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-04 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-05 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-04-06 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-04-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-04-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 8 | Action items identified in sprint retro | No
11 | Achieve process excellence | 2018-03-15 | 2019-04-09 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-04-10 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-04-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-04-12 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-04-13 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-04-14 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-04-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-04-16 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  | N/A |  | Yes
2019-08-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-08-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-08-01 | Score of TPR in a month | VER | Green |  | Green |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-01 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-01 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-01 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-08-01 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Project audit score | PPQA | 90 |  | 98.3 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-08-01 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-08-01 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-08-01 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-08-01 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-08-01 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  | N/A |  | Yes

## Sheet2
# | Project / Organization Objective | Created Date (MM/DD/YYYY) | Year Month (YYYY-MM) | Measurement Detail (Objective) | CMMI Process Area | Quantified Objective (Desired) | Information Need (Source) | Base Information (Actual) | Analysis on measurement (How to improve?) | Objective Achieved? (Calculated field) | Corrective Action Plan
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-01-02 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | Yes | as per need
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-04 | Number of risks occurred in a month | RSKM | 1 |  | 1 |  | Yes | as per need
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-01-05 | Number of customer escalations in a month | VER | 0 |  | 1 | Test on different environment and devices | No
6 | Achieve process excellence | 2018-03-15 | 2019-01-06 | Number of Configuration management non-conformities found in audit | CM | N/A
7 | Achieve process excellence | 2018-03-15 | 2019-01-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A |  |  |  |  | N/A (by Sprint)
10 | Achieve process excellence | 2018-03-15 | 2019-01-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 3 | - Lock requirement scope - Improve estimation | No
11 | Achieve process excellence | 2018-03-15 | 2019-01-09 | Number of tasks which exceeded original estimate | PP | 0 |  | 2 | - Lock requirement scope - Improve estimation | No | Depends
12 | Achieve process excellence | 2018-03-15 | 2019-01-10 | Project audit score | PPQA | 90 |  | 97.14 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-01-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-01-12 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-01-13 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes | perday depends on tasks
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-01-14 | Coding Practice Review score | VER | N/A |  |  |  |  | Discussion
20 | Achieve process excellence | 2018-03-15 | 2019-01-15 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  |  |  |  | AWS Services
2019-02-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-02-15 | Score of TPR in a month | VER | 90 |  | 95 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-02-15 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-02-15 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 1 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Project audit score | PPQA | 90 |  | 95 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-02-15 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-02-15 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-02-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-02-15 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes
2019-03-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-03-28 | Score of TPR in a month | VER | 90 |  | 93 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 1 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-03-28 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-03-28 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 3 | No action required. Proper plan update with justification was given. | No
11 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-03-28 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-03-28 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-03-28 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-03-28 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  | 2 |  | Yes
2019-04-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-04-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 1 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-04-02 | Score of TPR in a month | VER | 90 |  | 91 |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 3 | process updated to avoid this in future. | No
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-04 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-04-05 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-04-06 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-04-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-04-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 0 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-04-09 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-04-10 | Project audit score | PPQA | 90 |  | 98 |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-04-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-04-12 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-04-13 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-04-14 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-04-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-04-16 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  | N/A |  | Yes
2019-08-01
1 | Achieve excellence in test coverage | 2018-03-15 | 2019-08-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2 |  | 0 |  | Yes
2 | Achieve excellence in test coverage | 2018-03-15 | 2019-08-02 | Score of TPR in a month | VER | 90 |  | 95+ |  | Yes
3 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-03 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  | 0 |  | Yes
4 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-04 | Number of risks occurred in a month | RSKM | 0 |  | 0 |  | Yes
5 | Achieve high customer satisfaction | 2018-03-15 | 2019-08-05 | Number of customer escalations in a month | VER | 2 |  | 0 |  | Yes
6 | Achieve process excellence | 2018-03-15 | 2019-08-06 | Number of Configuration management non-conformities found in audit | CM | 1 |  | 0 |  | Yes
7 | Achieve process excellence | 2018-03-15 | 2019-08-07 | No of tailorings in project during the execution of project - in a year | IPM | N/A
10 | Achieve process excellence | 2018-03-15 | 2019-08-08 | Number of days release/work product was delayed from schedule | PMC | 1 |  | 0 |  | Yes
11 | Achieve process excellence | 2018-03-15 | 2019-08-09 | Number of tasks which exceeded original estimate | PP | N/A
12 | Achieve process excellence | 2018-03-15 | 2019-08-10 | Project audit score | PPQA | Green |  | Green |  | Yes
13 | Achieve process excellence | 2018-03-15 | 2019-08-11 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0 |  | 0 |  | Yes
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-08-12 | No. of planned/schedule requirements against which component is not identified | RD | 0 |  | 0 |  | Yes
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2019-08-13 | No. of features / CRs without acceptance criteria | REQM | 0 |  | 0 |  | Yes
18 | Promote best coding practices among peers | 2018-03-15 | 2019-08-14 | Average number of peer reviews conducted in a week per developer | VER | 2 |  | 2 |  | Yes
19 | Software development with highest standards of code quality | 2018-03-15 | 2019-08-15 | Coding Practice Review score | VER | N/A
20 | Achieve process excellence | 2018-03-15 | 2019-08-16 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | N/A |  | N/A |  | Yes

## Template PakWheels_ Measures-Gu
# | Project / Organization Objective | Created Date (MM/DD/YYYY) | Year Month (YYYY-MM) | Measurement Detail (Objective) | CMMI Process Area | Quantified Objective (Desired) | Information Need (Source) | Base Information (Actual) | Analysis on measurement (How to improve?) | Objective Achieved? (Calculated field) | Corrective Action Plan
1 | Achieve excellence in test coverage | 2018-03-15 | 2018-03-01 | Number of escaped defects occurred in a month (where team is owner of production deployment) | VAL | 2
2 | Achieve excellence in test coverage | 2018-03-15 | 2018-03-01 | Score of TPR in a month | VER | 90
3 | Achieve high customer satisfaction | 2018-03-15 | 2018-03-01 | Number of hot fixes in a month (where team is owner of production deployment) | PP | 1 |  |  |  |  | as per need
4 | Achieve high customer satisfaction | 2018-03-15 | 2018-03-01 | Number of risks occurred in a month | RSKM | 0 |  |  |  |  | as per need
5 | Achieve high customer satisfaction | 2018-03-15 | 2018-03-01 | Number of customer escalations in a month | VER | 0
6 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of Configuration management non-conformities found in audit | CM | 1
7 | Achieve process excellence | 2018-03-15 | 2018-03-01 | No of tailorings in project during the execution of project - in a year | IPM | N/A |  |  |  |  | N/A (by Sprint)
8 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of issues identified in integration tests | PI | 0
9 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Minimum Number of times integration tests executed | PI | 1
10 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of days release/work product was delayed from schedule | PMC | 1
11 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of tasks which exceeded original estimate | PP | N |  |  |  |  | Depends
12 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Project audit score | PPQA | 90
13 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of open high priority risks identified in a month (for which mitigation is not started) | RSKM | 0
14 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of impact analysis not done for CR | TS | 0
15 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Number of TDD not updated against CRs in a month | TS | 0
16 | Ensuring alignment of development with requirements | 2018-03-15 | 2018-03-01 | No. of planned/schedule requirements against which component is not identified | RD | 0
17 | Ensuring alignment of development with requirements | 2018-03-15 | 2018-03-01 | No. of features / CRs without acceptance criteria | REQM | 0
18 | Promote best coding practices among peers | 2018-03-15 | 2018-03-01 | Average number of peer reviews conducted in a week per developer | VER | N |  |  |  |  | perday depends on tasks
19 | Software development with highest standards of code quality | 2018-03-15 | 2018-03-01 | Coding Practice Review score | VER | N/A |  |  |  |  | Discussion
20 | Achieve process excellence | 2018-03-15 | 2018-03-01 | Check once a year OS and hardware expiry dates mentioned in project plan | PP | 2 |  |  |  |  | AWS Services

## Cover Sheet
Author: Ali Raza Approved By: Usman Ali Ver #: 0.1
Ver # | Author | Details | Date | Approved By | Approval Date
0.2 | Ali | Corrective Action Plan against Measurement Plan | 2018-04-02 | Usman Ali | 2018-04-02
0.1 | Ali | Created Measurement sheet | 2018-01-01 | Usman Ali | 2018-03-15
Template: Author: Bilal Bin Zafar Approved By: Usman Ali Ver #: 2.0
Ver # | Author | Details | Date | Approved By | Approval Date
2 | Bilal Bin Zafar | Added KPI of Servers OS and Hardware review | 2018-12-01
2 | Bilal Bin Zafar | Removed on KPI and made one KPI optional | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | Added column "Is Mandatory?" to be part of template | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | Added template sheet | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | 1. Removed crossed out items from M&A template sheet 2. Updated column name "Month" to "Year-Month" and updated its date to format YYYY-MM 3. Added column "CMMI Process Areas" with PA codes 4. Added new M&A items and their respective formulas 5. Removed sheet "Common Objectives" 6. Updated column names to reflect column meaning 7. Removed "Dervied information" column 8. Renamed "Mitigation plan" column to "Corrective Action Plan" | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | Added "Objective Achieved" Column with their formulas | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | Removed columns and update the template | 2018-12-01 | Usman Ali | 2018-12-01
2 | Bilal Bin Zafar | Created Measurement sheet | 2018-12-01 | Usman Ali | 2018-12-01